## Sheet1
Column1 | Postion & Duration | Column3
A | Based on the initiation diagram | Initiation
B | A+12 days | Selection
C | B+2 | Meeting validation
D | C+3 | Operational Initiation and verification of BC
E | D+8 | Financial initiation and Veriification of BC
F | E+3 | Authorisation of Commitment
G | F+2 | Send and Receive counter signed order forms
H | F+5 | Send Invitations
I | H-J | Arrangement of Logistics
J | K-5 | Finalise Logistics
K | Event start - Event end | Event
L | K+3 | Submit the attendance list
M | K+15 | Pre invoice check
N | M+2 | Promt initial de-commitement
O | M+5 weeks | Invoice initiation and payment
P | K+20 weeks | Reimbursement
Q | P+5 | Final De-commitment